## Bug Audit Summary
SocialShield App - Bug Audit & Verification Report
Bug ID | Component | Severity | Description | Root Cause | Solution | Status
BUG-01 | Image Scan Module | HIGH | Image scan loading spinner spins forever without returning or navigating to results. | Concurrent state modifications in Provider notification routines during navigation callbacks, combined with lack of network timeouts. | Wrapped route triggers inside WidgetsBinding.instance.addPostFrameCallback and set explicit Dio timeouts to 60s to cover Render cold starts. | COMPLETED
BUG-02 | Connectivity Service | MEDIUM | Text and URL scan processes show false 'No Internet Connection' errors despite connection active. | DNS lookup check used for offline testing failed consistently on emulator environments due to lookups on local host addresses. | Removed DNS lookup checking. Implemented dynamic direct connection ping fallback inside scan repository. | COMPLETED
BUG-03 | Firebase Auth | HIGH | Login/register credentials expire quickly showing 'Auth credential incorrect, malformed, or expired'. | Access tokens retrieved from Firebase were cached statically in Dio headers, failing to renew upon token expiration. | Added dynamic Firebase token refresh using FirebaseAuth.instance.currentUser?.getIdToken() inside auth client interceptors. | COMPLETED
BUG-04 | Result Screen UI | MEDIUM | Layout shows RenderFlex Overflow errors and raw formula strings like \${result!.confidence}%. | Hardcoded row sizes and escaped characters in text display templates. No scroll physics on smaller screens. | Restructured screen with SingleChildScrollView and expanded elements, fixing double escapes in string interpolations. | COMPLETED
BUG-05 | Dashboard Screens | LOW | Total scan counters on the dashboard are out of sync and don't match scan history. | Count values were mapped from static fields in User Profiles rather than actual collection count query streams. | Refactored DashboardProvider to aggregate total, safe, and threat counts dynamically from real-time scan history stream. | COMPLETED